## Gantt Chart
[39 empty] | Project Name | Mobile Applicatation Development
[39 empty] | Project Manager's Name | Ted Pettit
D Cal | Stage | Start Date | Target Days For Completion | Target End Date | End Date | Actual Days taken | 2016-01-01 | 2016-01-02 | 2016-01-03 | 2016-01-04 | 2016-01-05 | 2016-01-06 | 2016-01-07 | 2016-01-08 | 2016-01-09 | 2016-01-10 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-16 | 2016-01-17 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-23 | 2016-01-24 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-01-30 | 2016-01-31 |  | Project Description | Mobile Application development for Sales team to track their daily activities.
| Gathering Requirements | 2016-01-01 | 3 | 2016-01-03 | 2016-01-03 | 3
-1 | Planning | 2016-01-04 | 5 | 2016-01-08 | 2016-01-09 | 6
| Research | 2016-01-08 | 4 | 2016-01-11 | 2016-01-11 | 4
| Designing | 2016-01-11 | 5 | 2016-01-15 | 2016-01-15 | 5
| Developing Module 1 | 2016-01-16 | 4 | 2016-01-19 | 2016-01-19 | 4
1 | Developing Module 2 | 2016-01-20 | 3 | 2016-01-22 | 2016-01-21 | 2 | [31 empty] | 9
| Testing Period | 2016-01-22 | 2 | 2016-01-23 | 2016-01-23 | 2
-1 | Work on Feedbacks | 2016-01-24 | 4 | 2016-01-27 | 2016-01-28 | 5
| Final Submission | 2016-01-28 | 2 | 2016-01-29 | 2016-01-29 | 2
#VALUE!
6 | 1 | 2 | 9 |  | 9 | Stage: 'Final Submission' is completed. | 2016-01-04: Total 9 Stages Completed. And, Out of 9 complete stages; 2016-01-06: 6 Stages are completed on projected time.; 2016-01-07: 1 Stage is completed before projected time.; 2016-01-08: 2 Stages are completed after projected time.
Powered By
ExcelChamps
Stage: 'Final Submission' is completed.
Total 9 Stages Completed. And, Out of 9 complete stages
6 Stages are completed on projected time.
1 Stage is completed before projected time.
2 Stages are completed after projected time.
More Templates
Mobile Applicatation Development
Project Manager's Name
Ted Pettit
Project Description
Mobile Application development for Sales team to track their daily activities.

## Other Useful Templates
Other Useful Templates